Schedule

Erasmus+ programme with Partner Countries

Mobility of Students and Teachers

Project no. 2024-1-PL01-KA171-HED-000198210

Duration: 1.08.2024 – 31.07.2026

TEACHERS

| February-April, 2025 May, 2025 June, 2025 July-December, 2025 October 2025 - June 2026 | – the process of selecting teachers to go to the Partner University in the academic year 2025/2026 (to/from the University of Rzeszów) - sending the teachers selection protocol to the University of Rzeszów (the main and reserved lists, list of unclassified candidates and reasons of rejection should be kept in the Sending Institution). - informing selected teachers by the host University about the application procedure and required documents - sending documents of teachers to the receiving University - sending signed documents and invitation letters by the receiving University to selected teachers - Teachers Mobility - preparation for mobility (insurance, visa, etc.) - Teachers incoming to the University of Rzeszów - arrival to Rzeszów – min. one day before the mobility - first day of the mobility – meeting with the Erasmus+ institutional coordinator in order to sign the individual agreement and receive Erasmus+ grant and meeting with the responsible person of the visit at the faculty - 5 days of didactics - last day of the mobility - meeting with the Erasmus+ institutional coordinator in order to sign financial document - min. one day after the mobility – departure - submission the online EU survey - Teachers outgoing from the University of Rzeszów – a few days before the mobility, meeting with Erasmus+ institutional coordinator in order to sign the individual agreement and receive Erasmus+ grant - 5 days of didactics at the partner University - after the mobility - meeting with the Erasmus+ institutional coordinator in order to sign financial document - submission the online EU survey |
| --- | --- |

STUDENTS

| February-April, 2025 May 1-20, 2025 May 20-21, 2025 till May 31, 2025 till October 31,2025 July-December, 2025 September 2025 – January/February 2026 The ending of study | – the process of selecting students to go to the Partner University in the academic year 2025/2026 (to/from the University of Rzeszów) - sending the students selection protocol to the University of Rzeszów (the main and reserved lists, list of unclassified candidates and reasons of rejection should be kept in the Sending Institution). - informing selected students by the host University about the application procedure and required documents - sending application forms and other documents of students to the receiving University (for winter semester) - sending application forms and other documents of students to the receiving University (for summer semester) - sending signed documents and invitation letters by the receiving University to students Student Mobility - students preparing to the mobility in the academic year 2025/2026 (insurance, visa, etc.) - arrival of students to the receiving University min. one day before the beginning of second semester - first day of semester at the University of Rzeszów – student’s meeting with the person responsible for incoming students (signing the individual agreement, payment of the 90% of scholarship by cash) and meeting with the departmental coordinator - the meeting of Polish students with the person responsible for incoming students and with the departmental coordinator of the receiving University - study mobility period - the ending of study at the faculty – receiving documents - submission the online EU survey - the payment of 10% of the scholarship for students after bringing to the Erasmus+ institutional coordinator of the University of Rzeszów documents issued by the departmental coordinator |
| --- | --- |